## Timestamps
Zeiterfassung TRex Game
[5 empty] | L. Roth | D.Hoyer | Total
Date: | Name: | Task: | Hours spent: |  | 47.4 | 37.75 | 91.15
2022-10-04 | D. Hoyer | Bitmap basics investigation | 1.5 | h
2022-10-07 | D. Hoyer | bitmap züg | 1.5 | h
2022-10-07 | L. Roth | Display allgemein | 1.5 | h
2022-10-10 | D. Hoyer |  | 1 | h
2022-10-10 | L. Roth |  | 1 | h
2022-10-11 | L. Roth | Structs and header files | 0.5 | h
2022-10-14 | D. Hoyer |  | 1 | h
2022-10-14 | L. Roth | structs, videos zu objectorientiert code in c | 1 | h
2022-10-20 | L. Roth | Scheiss Mongo Bmp | 4 | h
2022-10-20 | L. Roth | Nomal Bmp probiert | 1.5 | h
2022-10-25 | L. Roth | Worked on Bmp problem | 2 | h
2022-10-25 | D. Hoyer | Worked on Bmp problem | 2 | h
| S. Methner | Created Bmp converter | 6 | h
2022-10-28 | D. Hoyer | Problem mit de Farbe -> T-Rex farbig success | 1.5 | h
2022-10-28 | L. Roth | Problem mit de Farbe -> T-Rex farbig success | 1.5 | h
2022-10-30 | D. Hoyer | state machine und touch input | 3 | h
2022-10-31 | D. Hoyer | touch input | 1.5 | h
2022-10-31 | L. Roth | öppis | 1.5 | h
2022-11-04 | L. Roth | Eventhandling, Corrections | 2 | h
2022-11-05 | L. Roth | Some Improvements | 0.5 | h
2022-11-07 | L. Roth | Move and Shift function, U süsch zügs | 1.8 | h
2022-11-08 | L. Roth | Added the tree obstacle, Timer function and moved tree | 1.3 | h
2022-12-01 | D. Hoyer | Buffer überprüft, HW lässt nicht zu! | 1.75 | h
2022-12-02 | L. Roth | lcd angeschaut | 0.5 | h
2022-12-02 | D. Hoyer | move function studiert | 1 | h
2022-12-09 | D. Hoyer | move function lösung gefunden, nicht fertig | 1.5 | h
2022-12-09 | D. Hoyer | move function git gloub problem | 2 | h
2022-12-12 | D. Hoyer | move function chunnt guet! | 4 | h
2022-12-13 | D. Hoyer | move & border list funktioniert! | 2.5 | h
2022-12-18 | L. Roth | Neue Code Struktur (include fiels etc) | 1 | h
2022-12-30 | L. Roth | Projekt neu überarbeitet, Eigete Object library geschriebn für das schnellere laden der bmp datein, game Funktioniert soweit, jetzt noch verfeinerungen nötig. | 11 | h
2023-01-04 | L. Roth | Probiert schneller zmache | 1.3 | h
2023-01-04 | D. Hoyer | Score funktioniert und jump angepasst | 2.5 | h
2023-01-05 | D. Hoyer | Jump isch schön und random funktioniert | 1.5 | h
2023-01-07 | D. Hoyer | boarder collition tuet abr spinnt | 3 | h
2023-01-10 | D. Hoyer | collition funktioniert, lagt abr | 2 | h
2023-01-12 | L. Roth | Redesigned the CreatBorder function Worked on the collision fucntion. Redesigned the DrawBmp fucntion Created the SortBmp and CreateEdge function | 5.5 | h
2023-01-13 | D. Hoyer | Trex selection is done and works + Pause button works | 3 | h
2023-01-14 | L. Roth | Worked on Collisiond etection | 4 | h
2023-01-15 | L. Roth | Collision detection. Reworked border detection. Redraw bmp files | 4 | h